## Jan'24
Date reported | Unit | Reported by | Request Type | Location | Description | Progress Notes | Start Date | Completed
2023-12-19 | 8D | Peter Lewis | other | 8D | Ceiling leak in living/dining rm | Crown Roofing | 2023-12-19 | 2023-12-18
2023-12-26 | 17D | Terry Ruff | other | CH | Grill Night Dec 31 and Jan 1 at pool area. Need propane tanks for 1 grill and spare tanks. Also 5 round tables w/chairs in CH | completed | 2023-12-26 | 2023-12-29
2023-12-26 | 5B | Patricia Corsello | other | 5B | teeny ants in master bathroom and outside door. | NaturZone scheduled | 2023-12-26 | 2024-01-02
2024-01-02 | 25C | Joan Martin | Irrigation | Bldg 25 | sprinklers at 25ABCD don't seem to be on. | pump not working, checked by BV | 2024-01-02 | 2024-01-04
2024-01-03 | 5D | Steve Barnum | Grounds | pond 1 | the pond fountain on pond 1 is laboring again and probably needs to be cleaned. | has ben checked, water level too high. | 2024-01-03 | 2024-01-04
2024-01-03 | 3E | Nan Schreier | Fountain | pond 1 | don't know if anyone had noticed, but the founatin on lake 1 is fading. Spray is getting lower every day. | has been checked, water level is too high. | 2024-01-03 | 2024-01-04
2024-01-01 | 17D | Terry Ruff | Electrical | CH | LED light on CH, pool side, one toward south is not working. | replaced | 2024-01-01 | 2024-01-04
2024-01-02 | 8AB | Nan Schreier | Grounds | 8AB | there is a pile of yard waste across from the driveway from 8AB that needs to be removed. | removed | 2024-01-02 | 2024-01-04
2024-01-04 | 11A | Bob | Electrical | mulitple | change out lights in carport or street | replaced bldg 11,25,22,24 | 2024-01-04 | 2024-01-04
2024-01-03 | 14A | Chieko | other | 14A | pressure wash privacy garden door. Trim shrubs covering bldg address | completed | 2024-01-03 | 2024-01-03
2024-01-04 | 25A | Bob | Electrical | 25A | two lights shining across lake. | turned lights upward | 2024-01-04 | 2024-01-04
2024-01-04 | 10E | Bob | other | 10E | green cover on fence across from 10E is down | installed | 2024-01-04 | 2024-01-04
2024-01-04 | 27A | Valerie Harvey | Grounds | 27A | please put some new crushed shell or stones to entrance from carport area to front gate of privacy garden | installed shell | 2024-01-04 | 2024-01-04
2024-01-04 | 2C | Rosie Roncone | Carport | 2C | locking door handle on our carport storage closet keeps getting stuck. | WD40 applied | 2024-01-04 | 2024-01-05
2024-01-05 | 31G | Bob | Electrical | 31G | Light not working 11G wall, 5F ground | replaced bulbs | 2024-01-05 | 2024-01-05
2024-01-05 | 11F | Bob | other | Bldg 11/12 | hole in ground from tree removed behind 11/12 | filled in | 2024-01-05 | 2024-01-05
2024-01-05 | 1A | Bob | other | grounds | all garbage cans with white paintneed to be repainted and chains | completed | 2024-01-05 | 2024-01-05
2023-12-28 | 32G | Suzie Mandsager | Pool area | pool area | the lock on the west gate by the hot tub is sticking open so gate won't lock | WD40 all gates | 2023-12-28 | 2023-12-29
2023-12-28 | 32G | Suzie Mandsager | Electrical | 32EH | light on left side courtyard entrance pillar has broken glass/pane | replaced glass | 2023-12-28 | 2023-12-29
2023-12-28 | 11B | Ann Huhn | Grounds | 11B | our patio foundation area has black mold all over and really looks in poor condition. Please pressure wash | pressure washed | 2023-12-28 | 2024-01-09
2024-01-03 | County | Fire Dept | Grounds | multiple | 10F extinguisher not properly charged, 19F extinguisher blocked by plants, 4Faddress blocked by bushes | plants moved, shrubs trimmed, ext. replaced | 2024-01-03 | 2024-01-10
2024-01-04 | 22D | Joe Kirsche | other | CH | please set up CH for finance Comm mtg | set up | 2024-01-04 | 2024-01-08
2024-01-04 | 32G | Suzie Mandsager | pool area | spa | hot tub is foaming excessively | Added chlorine/chems. | 2024-01-04 | 2024-01-05
2024-01-05 | 3E | Nan Schreier | other | 3E | we have no power in our courtyard. Fountain off and lights too | turned on breaker | 2024-01-05 | 2024-01-08
2024-01-08 | 1E | Bob | Plumbing | 1E | fountain not working | replaced parts | 2024-01-08 | 2024-01-08
2024-01-08 | 29C | Bob | Electrical | 29C | 29C wall, 7E carport wall, 2D wall, 19G post, 18C wall, 18B ground, 12C carport wall, lights out | replaced bulbs | 2024-01-08 | 2024-01-08
2024-01-09 | 25A | Bob | Electrical | 25A | lights out 25A post, 30D wall -3 ground lights | replaced bulbs | 2024-01-09 | 2024-01-09
2024-01-07 | 19,4,6,7 | Judy Hundley | grounds | multiple | 19EH, 4EH, 6EH, 7EHplease spray the courtyards for weeds | sprayed | 2024-01-07 | 2024-01-09
2024-01-07 | 1E | Judy Hundley | other | 1E | outside wall facing street needs some mortar filled in and painted | patched and painted | 2024-01-07 | 2024-01-08
2024-01-08 | 3AB, 10EF | Nan Schreier | fountain | 3AB, 10EF | both fountains are off | working now | 2024-01-08 | 2024-01-11
2024-01-09 | Maint | Nan Schreier | Grounds | maint. Area | please remove pile of green waste we left just north of the area along the driveway | removed | 2024-01-09 | 2024-01-10
2024-01-09 | 10F | Linda Kebler | Electrical | 10F | one light by pond 2, bldg 14 is out. | replaced bulbs | 2024-01-09 | 2024-01-10
2024-01-10 | 3AB, 10EF | Bob | Grounds | 3AB, 10EF | trimmed palms 3A, 7E, 8A, 11E | trimmed palms | 2024-01-10 | 2024-01-10
2024-01-10 | 11B | Ann Huhn | Grounds | 11B | lanai flooding. not draining | built earth berm barrier and covered with shell
2024-01-10 | 27B | Valerie Harvey | Grounds | 27B | 27B entrance to privacy garden needs to have mud removed and stones or shell placed. Stump removed from recent tree cut down. | added shell, removed stump | 2024-01-10 | 2024-01-10
2024-01-10 | 22B | Barbara Ellen | other | 22B | please clean out gutter or tubes that run water down sides of bldg on back yard side. Water pooling. | cleaned out leaves | 2024-01-10 | 2024-01-10
2024-01-07 | CH | Judy Hundley | other | CH | please set up for Maint. Comm. Mtg Tuesday 1/16 | set up | 2024-01-07 | 2024-01-08
2024-01-07 | 3E | Nan Schreier | other | 3E | we need an additional garbage can for 3AB/4AB we have 5 overflowing this evenin | added can | 2024-01-07 | 2024-01-10
2024-01-07 | 21H 31E | Judy Hundley | other | 21H, 31E | galvanized covers running up bldg wall for AC's. please paint. | painted | 2024-01-07 | 2024-01-10
2024-01-07 | 19C,D | Judy Hundley | other | 19CD | storage shed doors need to be cleaned 19C and D | cleaned doors | 2024-01-07 | 2024-01-10
2024-01-10 | Bldg 4 | Nan Schreier | Grounds | Bldg 4 | moldy mess on the outside wall across the driveway from bldg 4 in the little park area, needs pressure washed | cleaned | 2024-01-10 | 2024-01-10
posted 1/12
2024-01-01 | Carports | Bob n Jorge | Electrical | Carports | All carports fitted with new lights | all carports complete | 2024-01-01 | 2024-01-12
2023-12-27 | 22C | Kathy Mull | other | CH | please take down Christmas tree on wed 1/3. also will need ladders for volunteers to remove decorations . | completed | 2023-12-27 | 2024-01-03
2023-12-27 | 22C | Kathy Mull | other | CH | please have all round tables and 2 lrg tables plus chairs set up for Italian Night 1/12. | comppleted | 2023-12-27 | 2024-01-11
2024-01-04 | 3D | Eric Schroeder | other | 3D | front balcony railing needs to be repaired or replaced. Entry stairs need to be painted or replace some tiles on landings. Courtyard - one loose paver stone in front of first step to our stairs, center. | cleaned balcony. Painted stairs. Fixed paver | 2024-01-04 | 2024-01-05
2024-01-08 | 8D | Agnes Lewis | Grounds | 8D | please have BV trim green space behind bldg 8 | trimmed palms | 2024-01-08 | 2024-01-09
2024-01-08 | CH | Judy Hundley | Electrical | CH | please install new waterproof covers for the electrical outlet junction boxes on the roof area where christmas lights plug in. | replaced | 2024-01-08 | 2024-01-10
2024-01-08 | 32G | Suzie Mandsager | other | pool area | need a big, sturdy heavy trash container in the pool area by the shower. | replaced w/ new container | 2024-01-08 | 2024-01-12
2024-01-11 | gate | Nan Schreier | electrical | gate area | large light on left of entrance wall by gate is out again. Also lights on gatehouse are on at 9:25am. Seems issues are not resolved. | lights are on 2 different photo cells. Daylight gits different, and cloudy weather can affect also. | 2024-01-11 | 2024-01-15
2024-01-13 | 15H | Bob Shattuck | Electrical | 15H | under craport light 15FH is burned out. Pleased put LED light there as our car was vandalized last yr while parked there.also light in storage area for 15H only works at night when carport lights go on. | replaced fixture. Storage is electrical - need electrician. | 2024-01-13 | 2024-01-12
2024-01-13 | 30A | Phyllis Sellers | other | pool area | tiles around pool are filthy black with scum. They need to be scrubbed. Pool bottom has lots of tree debris from Tues. storm. Pool maint was here twice and totally ignored the work that needs done. | cleaned | 2024-01-13 | 2024-01-15
2024-01-13 | 17C | Donna Brown | Grounds | 17C | please arrange to have the palm berries (seeds) in bunches over our stairs cut down. They are constantly falling or blowing down on the staits and are a hazard and a mess. TY | removed | 2024-01-13 | 2024-01-17
2024-01-12 | 8E | Maureen O'Brien | Grounds | 8E | the palm tree in our courtyard 8E-G side is infected with Ganaderma, confirmed by Ingrid. I am asking BV to remove and reduce stump as low as posible. Other shrubs should be left. | removed | 2024-01-12 | 2024-01-16
2024-01-12 | 8E | Maureen O'Brien | Electrical | 8E | is it possible to switch out the extremely bright LED light bulb in our carport space C to something of lower wattage? It is not only bright we get 2 lights due to the reflection off the car. | new LED lighting installed per security committee and board. ALL to be the same, uniform lighting. | 2024-01-12 | 2012-01-15
2024-01-13 | 15D | Tanya Gubin | Grounds | 15AD | request to repair drain near house no 15AD. The drain hole is clogged with soil and water cannot sep into drain pipes. When it rains, water collects at the storage door and sometimes flows inside. Also flodding flower beds. | connected diverter pipe to downspout | 2024-01-13 | 2024-01-15
2024-01-15 | Var | Bill | Carports | various | please push the carport lights in tighter to the ceiling. 24 + 25, check others. | tighten up and caulk | 2024-01-15 | 2024-01-16
2024-01-15 | 27B | Valerie Harvey | Grounds | 27B | please take away extra mud from back of walkway to privacy garden. Also there is a pile of mud in front of carport near there that happened during rain. Also cement blocks at end of walkway that have been there for years, need removed. | completed multiple | 2024-01-15 | 2024-01-16
2023-11-21 | 25C | Joan Martin | Grounds | 25C | palm trees in courtyard and lanai area need pruning | trimmed palms | 2023-11-21 | 2024-01-17
2023-12-08 | 32G | Suzie Mandsager | Grounds | 32G | for BV crew, remind them on the weekly visits to cut off all "sucker" growths at the base of trees mainly ligustrums and carrotwoods. | BV removed | 2023-12-08 | 2024-01-17
2023-12-12 | CH | Sandra Rush | other | CH fitness | need lower shelf in fitness room, TV remote - can't reach if its up high | installed remote holder by light switch | 2023-12-12 | 2024-01-16
2023-12-21 | 22EG | Susan Maloof | other | 22G | landingfor 22G is coming apart. | patched and painted | 2023-12-21 | 2024-01-17
2024-01-05 | CH | Sandra Rush | Grounds | all | tree seedlings are growing into the street at the curbs. Also sevral by maintenance area, bldgs 20's. | removed | 2024-01-05 | 2024-01-17
2024-01-11 | 16C | Ellen Flaiz | Grounds | Bldg 16 | back of bldg 16. palm dfronds and lots of debris in gutters. 2 palm trees on bldg at 16D and 16H | trimmed palms | 2024-01-11 | 2024-01-16
2024-01-15 | 16B | Barbara Lessard | Irrigation | 16B | please replace sprinkler head on outside left of lanai door. | replaced | 2024-01-15 | 2024-01-16
2024-01-17 | 12B | Thomas Sweeney | other | CH | set up poker tables and chairs in main CH for poker tournament. 3 tables. | set up | 2024-01-17 | 2024-01-18
2024-01-05 | 26A | Brian Lang | Electrical | 26A | please replace light fixtures on the outdoor pato and storage unit. Outdoor unit is covered with paint. Indoor switch is inoperable. | replaced light fixture. | 2024-01-05 | 2024-01-18
2024-01-05 | 26A | Brian Lang | Grounds | 26A | please trim the large oak tree in front of 26A, the leaves are a nuisance. | cannot trim any further. Seasonal issue | 2024-01-05 | 2024-01-09
2024-01-15 | 20C | Sharon Sapienza | Grounds | 20C | there is a fan palm with branches pushing into my lanai screen | trimmed palms | 2024-01-15 | 2024-01-18
2024-01-15 | 20C | Sharon Sapienza | other | 20C | my assigned parking spot floods everytime it rains. I have to park in guest parking. Pool of water does not drain. | low spot in pavement. Not really fixable. | 2024-01-15 | 2024-01-16
2024-01-17 | 27H | Ingrid | Grounds | 21 | a tall palm by bldg 21 has several nails protruding from the trunk (most likely from christmas lights) need to be removed and not inserted again. | removed nails | 2024-01-17 | 2024-01-18
2024-01-17 | 17C | Donna Brown | other | 17C | I just wanted to say thank you very much for seeing so quickly to the work order I submitted last Saturday. Kudos to you and the team. | Happy to Help | 2024-01-17 | 2024-01-18
2024-01-18 | 25G | Beth Douglas | other | 25G | steps are stained from palm tree droppings, please clean or paint. | pressure washed | 2024-01-18 | 2024-01-18
2024-01-19 | 24A | Bob | Electrical | 24A | light out by lake 3 behind 24A | replaced fixture. Storage is electrical - need electrician. | 2024-01-19 | 2024-01-19
2024-01-18 | 6C | Joe LaForgia | Grounds | 6C | the trees are hitting the storage sheds that are located next to the carport. Also top of the storahe sheds needs to be cleaned as weeds are growing on the tiles. | trimmed, removed weeds | 2024-01-18 | 2024-01-19
2024-01-19 | 3EFGH | Bob | Plumbing | 3EFGH | Fountain needs cleaning | cleaned | 2024-01-19 | 2024-01-19
2024-01-19 | 5F | William Boychuk | Grounds | 5F | please blow off leaves and branches from the roof of bldg 5's carport and trim over hanging palm branches in rear of bldg 5 close to roof and bldg | blew off roof. Trimmed palm | 2024-01-19 | 2024-01-22
2024-01-21 | Gate | Judy Hundley | Electrical | gate area | bulb needed in sconce at front gate. Leaving property, it is the huge one located on right side | on different eye -Bob | 2024-01-21 | 2024-01-22
2024-01-21 | gate | Judy Hundley | Electrical | gate area | recepatcle cover, is loose and also installed upside down. Please remove and replace correctly so water will not enter. Located right side coming in from gate by water drain open area. | installed | 2024-01-21 | 2024-01-22
2024-01-21 | CH | Judy Hundley | other | pool area | pool post cover needs replaced. By bldg 30 gate side | replaced | 2024-01-21 | 2024-01-22
2024-01-21 | 7B | Judy Hundley | Grounds | 7B | carport 7B corner. Needs mortar/stucco/paint, large chunk missing | mortar and paint | 2024-01-21 | 2024-01-22
2024-01-21 | 2EF | Nan Schreier | grounds | 2EF | wall across from 2 EF. Electrical equip changed. Left old site very dirty and with holes in the wall. | painted | 2024-01-21 | 2024-01-22
2024-01-22 | CH | Terry Ruff | other | CH | need 8 tables with chairs for grill night Tuesday, 23rd. | set up | 2024-01-22 | 2024-01-23
2024-01-11 | 10H | Suzanne Gould | Grounds | 10H | there are a few spots where the paint and top layer of concrete have chipped off on the floor just outside the iron gate. | pressure washed and painted | 2024-01-11 | 2024-01-24
2024-01-11 | 16G | Henry Garcia | other | 16G | just getting back from NY and discovered water in our ceiling of the entry hallway. | Crown Roofing scheduled | 2024-01-11 | 2024-01-18
2024-01-11 | 26E | Valarie Evanko | Grounds | 26E | please have Bob or Jorge sweep off the shells that the rain washed onto the sidewalk near the mailboxes between bldg 25-26. | cleaned up | 2024-01-11 | 2024-01-16
2024-01-23 | 23A | Donna Ness | Grounds | 23A | palm tree full of falling berries in front between 23A and 24. | trimmed palms | 2024-01-23 | 2024-01-23
2024-01-23 | 22A | Bob | Electrical | 22A | light on all the time | replaced photo cell | 2024-01-23 | 2024-01-23
2024-01-23 | 17A | Bob | Electrical | 17A | light out 17A garden, behind 27A, behind 24A, | replaced bulbs or fixtures | 2024-01-23 | 2024-01-23
2024-01-23 | CH | Ingrid | other | CH | high back chair in CH, on the left side with back to dance floor. Loose leg on left front of chair | tightened leg | 2024-01-23 | 2024-01-24
2024-01-24 | 25H | Bob | other | 25H | stairs need painted | painted | 2024-01-24 | 2024-01-24
2024-01-04 | 27H | Ingrid Laszlo | Grounds | CH | please have BV trim the Arboricola in front of the clubhouse separating the bushes and keeoing a natiural shape | BV trimmed | 2024-01-04 | 2024-01-24
2024-01-24 | 20E | Bob | Plumbing | 20E | roof drain hose off | attached drin hose | 2024-01-24 | 2024-01-24
2024-01-24 | 28H | Leela Benford | other | 28H | please ask maint. Not to put trash cans at the corner of our carport by the storage. People drop trash by the cans later in the mrning and it will be overflwoing innto the parking area behind my car. | noted | 2024-01-24 | 2024-01-25
2024-01-25 | 6F | Joe Sacco | other | 6F | please clean and power wash columns, walls and underside of ceilings on carport for bldg 6 | cleaned spider webs. Can't power wash unless ALL vehicles are moved out | 2024-01-25 | 2024-01-25
2024-01-25 | 6F | Joe Sacco | other | CH | clean exhaust fans in mens bathroom in CH. Fan is caked with dust and debris | cleaned fan | 2024-01-25 | 2024-01-25
2024-01-23 | 14D | John Anderson | other | 14D | balconies have rotted wood on each side. | inspected but not scheduled for repair yet | 2024-01-23 | 2024-01-25
2024-01-23 | 10B | John Anderson | Electrical | Bldg 2 | new electrical box needs holes filled in and painted. Bldg 8 box still covering hole in elec box this must be repaired, water egtting in | filled in holes, painted. Caulked around box bldg 8. Bob | 2024-01-23 | 2024-01-23
2024-01-23 | 29B | Paula MacHose | Grounds | 29B | trim the tree found in te back of bldg 29 by the dryer vents. Its done flowering and needs trimmed about 3' from top. | BV/Bob trimmed | 2024-01-23 | 2024-01-24
2024-01-26 | 27 | Bob | Electrical | 27/28 | light not working between 27/28 | replaced light fixture. | 2024-01-26 | 2024-01-26
2024-01-26 | 12 | Bob | Grounds | 12 | Australian pine on curbs | removed | 2024-01-26 | 2024-01-26
Posted 1-26-24
2024-01-25 | 2E | Dorothy Cushman | other | 2E | our tap water has a very distinct amonia smell, boiling does not help.both hot and cold.no rust is observed | run all faucets for 10 minutes to flush lines | 2024-01-25 | 2024-01-26
2024-01-26 | 9EF | Nan Schreier | Grounds | 9EF | dead patch on a tree in front of 9EF | removed | 2024-01-26 | 2024-01-29
2024-01-29 | 9H | Patricia freidberg | Grounds | 9H | palm tree lakeside bldg 9 has 1 lrg branch hanging low on the ground, needs to be cut | removed branch | 2024-01-29 | 2024-01-30
2024-01-29 | 31D | GaryBazzano | Grounds | 31D | it would be great if they can trim the lrg palm adjacent to the top of our staircase and the small palm at the bottom. Also, pool view is being restricted due to a large palm in NE corner of the fence/pool area and some smaller plams south of lrg palm bush in corner | trimmed | 2024-01-29 | 2024-01-30
2024-01-29 | 31B | MaryKay Strachota | Grounds | 31B | the back of 31B needs to be cleaned up. Tree with broken limb needs removed plus debris on the ground. | trimmed | 2024-01-29 | 2024-01-30
2024-01-29 | 19EF | Nan Schreier | Fountain | 19EF | fountain is overfilled. Residents should not fill fountains. | drained | 2024-01-29 | 2024-01-29
2024-01-29 | 10D | Sabina Duborg | Grounds | 10D | two palm trees that abut our lanai's in back of bldg 10DC have branches that are hitting our screens, please remove | trimmed palms CD, GH | 2024-01-29 | 2024-01-30
2024-01-30 | 6C | Joe LaForgia | Grounds | 6C | Tops of sheds were not cleaned, please advise. Weeds growing. | cleaned | 2024-01-30 | 2024-01-31
2024-01-24 | 17H, 30D | Judy Hundley | Grounds | 17H, 30D | painting of steps needed at 17H and 30D. | painted | 2024-01-24 | 2024-01-31
2024-01-24 | 29G | Judy Hundley | other | 29G | storage shed vent replacement. Only replace with 12". Also replace old rusted screws. | painted | 2024-01-24 | 2024-01-25
2024-01-24 | 22B | Barbara ellen | irrigation | 22B | outside 22B the sprinkler seems buried in plants and is not offering irrigation when sprinklers turn on at night. | put extension on end | 2024-01-24 | 2024-01-25
2024-01-31 | CH | Bill/Terry Ruff | other | CH | grills need to be cleaned for upcoming Grill Night. Also check propane. Grill only working on one side, please check. | cleaned grills and picked up new tanks. | 2024-01-31 | 2024-01-31
2023-12-11 | 19G | John Mosteller | other | 19G | we need some screening put under our lanai screen frame to prevent bugs from coming into the unit. | installed material. Also same for 2C | 2023-12-11 | 2024-02-01

## Feb '24
Date reported | Unit | Reported by | Request Type | Location | Description | Progress Notes | Start Date | Completed
2024-02-02 | 22D | Joe Kirsche | other | 22D | roof leak, guest bedroom | Crown notified | 2024-02-02 | 2024-02-02
2024-01-25 | 17D | Terry ruff | other | CH | grill night set up please check grills, clean burners | set up, cleaned grills | 2024-01-25 | 2024-02-02
2024-01-25 | 24C | Paula struble | pressure wash | 24C | courtyards have accumulated a lot of dirt and green mildew on stucco and lmp posts and 2nd floor stairs. Please pressure wash | pressure washed, painted | 2024-01-25 | 2024-01-31
2024-01-30 | 22F | Barbara Nichols | Grounds | 22F | water pouring in front entrance, very dangerous for falling, sprinklers need to be adjusted | Jorge, changed angle | 2024-01-30 | 2024-01-31
2024-01-30 | 26F | Ron Schmutzlr | electrical | Gate | American flag outside front gate needs a brighter light at night. | installed new light | 2024-01-30 | 2024-02-02
2024-01-30 | 26F | Ron Schmutzlr | electrical | 26F | lamp post bulb is out at courtyard 26E-H | working now | 2024-01-30 | 2024-02-02
2024-02-02 | 26E | Val Evanko | other | CH | set up for meeting on Sat. | set up, cleaned grills | 2024-02-02 | 2024-02-02
2024-01-30 | 25A | Claudia Moore | electrical | 25A | pole light by garbage crib between 25A an 26F. Must be an outage soemwhere lake lights are out in back of 25A, also light out front of 26 E-H. | replaced panel on 24. | 2024-01-30 | 2024-02-06
2024-02-02 | 20E | Nan schreier | Grounds | 20E | black downspout extension needs to be shortened, please cut back to splash tray. | removed | 2024-02-02 | 2024-02-02
2024-01-30 | 27D | Bill | other | CH | Please address the front door of clubhouse as the front and inside look pretty dirty. Could also use a touch up of paint around the lock | painted doors | 2024-01-30 | 2024-02-06
2024-02-06 | 6A | Bob | other | 6A | paint strip on red bridge steps | painted doors | 2024-02-06 | 2024-02-06
2024-02-06 | 7F | Bob | other | 7F | replaced RF sign on couirtyards | replaced panel on 24. | 2024-02-06 | 2024-02-06
2024-01-22 | 1D | JC realty | other | 1D | need outside stairs painted | painted | 2024-01-22 | 2024-02-07
2024-01-28 | 26B | Graham | other | 26B | ghost ants in kitchen | added to next NaturZone service | 2024-01-28 | 2024-01-29
2024-01-28 | 32G | Suzie Mandsager | Grounds | entrance | 2x4 wood stakes along the Italian Cypress trees in the middle median entrance area are no longer providing support after hurricane damage 2 yrs ago. Please remove stakes | Landscape Comm.? | 2024-01-28
2024-01-28 | 32G | Suzie Mandsager | other | 32G | please add our phone numbers to the Vizcaya Resident Directory | added to next NaturZone service | 2024-01-28 | 2024-01-29
2024-01-31 | 8D | Peter Lewis | Grounds | 8D | repaint fountain - drain | painted | 2024-01-31 | 2024-02-08
2024-02-05 | 1EH | Judy Hundley | other | 1EH | concrete parking bumpers need painted in front of courtyard 1EH | painted | 2024-02-05 | 2024-02-08
2024-02-06 | 19C | Diane Massa | Grounds | 19C | the palm like bush immediately in front of may lanai is growing on top into the gutter in front of my lanai screen and blocking waterflow in gutter. | trimmed | 2024-02-06 | 2024-02-08
2024-02-06 | 6C | Joe LaForgia | other | CH | raccoons at pool over the weekend | removal scheduled | 2024-02-06 | 2024-02-08
2024-02-06 | 6C | Joe LaForgia | other | flag | please illuminate the American flag at our entrance, the light is on bu dark on the side | replaced light | 2024-02-06 | 2024-02-06
2024-02-07 | 27D | Bill Caples | safety/sec. | 11H | the pole light behind 11H could use a coat of paint | painted | 2024-02-07 | 2024-02-08
2024-02-08 | 11F | Bob | electrical | lake 3 | light by lake 3 out | replaced bulb | 2024-02-08 | 2024-02-08
2024-02-08 | 11F | Bob | other | 11F | pole light needs painting | painted | 2024-02-08 | 2024-02-08
| 17H 30D | Judy Hundley | Grounds | 17H, 30D | please put 17H and 30D on the list for stairs to be painted | painted |  | 2024-02-08
2024-01-30 | 25G | Beth Douglas | Pressure Wash | 25G | pressure washing is needed on outside of bldg by balcomies/patios and roof overhang. | pressure washed | 2024-01-30 | 2024-02-09
2024-02-06 | 17d | Terry ruff | other | CH | grill night set up fro sat 2-10. inside | set up, cleaned grills | 2024-02-06 | 2024-02-09

## posted 2-9 '24
Date reported | Unit | Reported by | Request Type | Location | Description | Progress Notes | Start Date | Completed
2024-02-02 | 22D | Joe Kirsche | other | 22D | roof leak, guest bedroom | Crown notified | 2024-02-02 | 2024-02-02
2024-01-25 | 17D | Terry Ruff | other | CH | grill night set up please check grills, clean burners | set up, cleaned grills | 2024-01-25 | 2024-02-02
2024-01-25 | 24C | Paula struble | pressure wash | 24C | courtyards have accumulated a lot of dirt and green mildew on stucco and lmp posts and 2nd floor stairs. Please pressure wash | pressure washed, painted | 2024-01-25 | 2024-01-31
2024-01-30 | 22F | Barbara Nichols | Grounds | 22F | water pouring in front entrance, very dangerous for falling, sprinklers need to be adjusted | Jorge, changed angle | 2024-01-30 | 2024-01-31
2024-01-30 | 26F | Ron Schmutzlr | electrical | Gate | American flag outside front gate needs a brighter light at night. | installed new light | 2024-01-30 | 2024-02-02
2024-01-30 | 26F | Ron Schmutzlr | electrical | 26F | lamp post bulb is out at courtyard 26E-H | working now | 2024-01-30 | 2024-02-02
2024-02-02 | 26E | Val Evanko | other | CH | set up for meeting on Sat. | set up, cleaned grills | 2024-02-02 | 2024-02-02
2024-01-30 | 25A | Claudia Moore | electrical | 25A | pole light by garbage crib between 25A an 26F. Must be an outage soemwhere lake lights are out in back of 25A, also light out front of 26 E-H. | replaced panel on 24. | 2024-01-30 | 2024-02-06
2024-02-02 | 20E | Nan schreier | Grounds | 20E | black downspout extension needs to be shortened, please cut back to splash tray. | removed | 2024-02-02 | 2024-02-02
2024-01-30 | 27D | Bill | other | CH | Please address the front door of clubhouse as the front and inside look pretty dirty. Could also use a touch up of paint around the lock | painted doors | 2024-01-30 | 2024-02-06
2024-02-06 | 6A | Bob | other | 6A | paint strip on red bridge steps | painted doors | 2024-02-06 | 2024-02-06
2024-02-06 | 7F | Bob | other | 7F | replaced RF sign on couirtyards | replaced panel on 24. | 2024-02-06 | 2024-02-06
2024-01-22 | 1D | JC realty | other | 1D | need outside stairs painted | painted | 2024-01-22 | 2024-02-07
2024-01-28 | 26B | Graham | other | 26B | ghost ants in kitchen | added to next NaturZone service | 2024-01-28 | 2024-01-29
2024-01-28 | 32G | Suzie Mandsager | Grounds | entrance | 2x4 wood stakes along the Italian Cypress trees in the middle median entrance area are no longer providing support after hurricane damage 2 yrs ago. Please remove stakes | Landscape Comm.? | 2024-01-28
2024-01-28 | 32G | Suzie Mandsager | other | 32G | please add our phone numbers to the Vizcaya Resident Directory | added to next NaturZone service | 2024-01-28 | 2024-01-29
2024-01-31 | 8D | Peter Lewis | Grounds | 8D | repaint fountain - drain | painted | 2024-01-31 | 2024-02-08
2024-02-05 | 1EH | Judy Hundley | other | 1EH | concrete parking bumpers need painted in front of courtyard 1EH | painted | 2024-02-05 | 2024-02-08
2024-02-06 | 19C | Diane Massa | Grounds | 19C | the palm like bush immediately in front of may lanai is growing on top into the gutter in front of my lanai screen and blocking waterflow in gutter. | trimmed | 2024-02-06 | 2024-02-08
2024-02-06 | 6C | Joe LaForgia | other | CH | raccoons at pool over the weekend | removal scheduled | 2024-02-06 | 2024-02-08
2024-02-06 | 6C | Joe LaForgia | other | flag | please illuminate the American flag at our entrance, the light is on bu dark on the side | replaced light | 2024-02-06 | 2024-02-06
2024-02-07 | 27D | Bill Caples | safety/sec. | 11H | the pole light behind 11H could use a coat of paint | painted | 2024-02-07 | 2024-02-08
2024-02-08 | 11F | Bob | electrical | lake 3 | light by lake 3 out | replaced bulb | 2024-02-08 | 2024-02-08
2024-02-08 | 11F | Bob | other | 11F | pole light needs painting | painted | 2024-02-08 | 2024-02-08
| 17H 30D | Judy Hundley | Grounds | 17H, 30D | please put 17H and 30D on the list for stairs to be painted | painted |  | 2024-02-08
2024-01-30 | 25G | Beth Douglas | Pressure Wash | 25G | pressure washing is needed on outside of bldg by balcomies/patios and roof overhang. | pressure washed | 2024-01-30 | 2024-02-09
2024-02-06 | 17d | Terry Ruff | other | CH | grill night set up fro sat 2-10. inside | set up, cleaned grills | 2024-02-06 | 2024-02-09